Pilot Success Criteria & Scorecard

Brightwater Health Partners × Ridgeline Software
        Pilot units: St. Anne's 4 West and 5 East · Duration: 4 weeks

Purpose

Discharge acceleration and capacity visibility for med-surg units, starting with 4 West and 5 East at St. Anne's and expanding to all three hospitals. This document defines what "success" means before the pilot starts, so the go/no-go decision is made against numbers everyone agreed to up front.

Success criteria

Criterion

Baseline

Target

How measured

Owner

Discharge-to-departure time

5.2 hours

Under 3.5 hours

ADT discharge order to departure timestamp

Samantha Cole

Discharges before noon

14%

30%

Share of discharges with departure before 12:00

Tanya Ellis

Nurse manager time chasing status

6.0 hrs/week

Under 3.0 hrs/week

Weekly self-reported time log

Tanya Ellis

Decision rule: the pilot succeeds if at least two of the three criteria reach target by the final readout, and InfoSec completes its risk assessment with no high findings.

Scope

•	
      Read-only Epic ADT feed in the test environment, then production after InfoSec sign-off

•	
      Discharge milestones: order signed, medications ready, transport requested, education complete, departed

•	
      Automated handoffs to transport and pharmacy

Out of scope

•	
      Write-back to Epic

•	
      Perioperative scheduling

•	
      Units outside 4 West and 5 East

Timeline and readouts

Week

Milestone

0

Kickoff, baseline confirmed, ADT feed connected in test

1

Week 1 readout (Samantha, Tanya, Alex)

2

Week 2 readout; InfoSec responses delivered

4

Final readout to the Capacity Steering Committee; go/no-go

Sample document for the myBivy demo workspace. All organizations and people are fictional.