## Plan
# | Task | Workstream | Owner | Start wk | End wk | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1 | Executive kickoff | Kickoff | Alex Morgan / Rachel Summers | 1 | 1 | Complete | bar: W1
2 | Success metrics and rollout waves confirmed | Kickoff | Hannah Price / Jason Albright | 1 | 1 | Complete | bar: W1
3 | Store hierarchy and district mapping | Requirements | Ben Ortiz / Aisha Grant | 1 | 2 | Complete | bar: W1 to W2
4 | Manhattan WMS and Oracle Retail read access | Requirements | Ben Ortiz / Aisha Grant | 2 | 2 | Complete | bar: W2
5 | Out-of-stock alert thresholds by category | Requirements | Ben Ortiz / Luis Moreno | 2 | 2 | Complete | bar: W2
6 | Configure Southeast region (62 stores) | Implementation | Ben Ortiz | 2 | 3 | In progress | bar: W2 to W3
7 | Data validation with IT Applications | Implementation | Aisha Grant | 3 | 3 | In progress | bar: W3
8 | Pilot-store cutover to production | Implementation | Ben Ortiz / Jason Albright | 3 | 3 | Planned | bar: W3
9 | Train-the-trainer session | Training | Hannah Price / Kate Donnelly | 3 | 3 | Planned | bar: W3
10 | District manager training, Southeast | Training | Kate Donnelly | 4 | 4 | Planned | bar: W4
11 | Southeast go-live | Go live | Ben Ortiz / Jason Albright | 4 | 4 | Planned | bar: W4
12 | Configure Central region (58 stores) | Wave 2 | Ben Ortiz | 5 | 7 | Planned | bar: W5 to W7
13 | Central go-live | Wave 2 | Jason Albright | 8 | 8 | Planned | bar: W8
14 | Configure Northeast region (60 stores) | Wave 3 | Ben Ortiz | 9 | 11 | Planned | bar: W9 to W11
15 | Northeast go-live | Wave 3 | Jason Albright | 12 | 12 | Planned | bar: W12
16 | 30-day value review | Value | Hannah Price / Rachel Summers | 8 | 8 | Planned | bar: W8